## Project Plan and Gantt
Project Name | Government id card registrsation
Project Manager | Dinesh kumar
Project Deliverable
Scope Statement:
Start Date | 2017-01-24
End Date | 2017-04-14
Overall Progress
Tasks | Responsible | Start | End | Days | Status
Set kick-off meeting | Amir | 2017-01-24 | 2017-01-25 | 1 | complete
Agree on objectives | vijayakumar | 2017-01-25 | 2017-01-29 | 4 | Complete
Detailed Reqs. | rakesh | 2017-01-29 | 2017-02-03 | 5 | complete
Hardward Reqs. | rakesh | 2017-02-03 | 2017-02-05 | 2 | complete
Final Resource Plan | rakesh | 2017-02-05 | 2017-02-09 | 4 | complete
Staffing | Amir | 2017-02-09 | 2017-02-10 | 1 | complete
Techincal Reqs. | vijayakumar | 2017-02-10 | 2017-02-14 | 4 | In progress
DB Development | Dineshkumar | 2017-02-14 | 2017-02-16 | 2 | In progress
API Development | Dineshkumar | 2017-02-16 | 2017-02-20 | 4 | In progress
UI Client | Amir | 2017-02-20 | 2017-02-24 | 4 | In progress
Testing | vijayakumar | 2017-02-24 | 2017-03-04 | 8 | In progress
Dev. Complete | rakesh | 2017-03-04 | 2017-03-07 | 3 | pending
Hardware Config. | Amir | 2017-03-07 | 2017-03-09 | 2 | pending
System Testing | vijayakumar | 2017-03-09 | 2017-03-12 | 3 | pending
Launch |  | 2017-03-12 | 2017-03-13 | 1

## Stakeholder List
Stakeholder List
Name | Position | Role in project | Email address | Requirements | Expectations
Vijayakumar | VP of Product | Final approval of milestones | vj@gmail.com | Downtime of no longer than 20 minutes | QA to take less than 1 week, marketing to promote new features in newsletter
Aamir | Business Analyst | Collects the Requirements | aamir@gmail.com | Query the customer to find the exact requirements of the project | Deal the customer by querying him to find his exact requirements
Rakesh | Design | Deals with high level and low level design | rk@gmail.com | Design for the project considering the input as requirements | Design the project within the planned time
Dinesh Kumar | Project Manager | Manages the project and revise the product | dk@gmail.com | Follow the entire team till the completion of the project | Maintain and help the team whenever problem occurs in the project team

## Communication Plan
Communication Plan
Communication Type | Deliverable | Description | Delivery Method | Frequency | Owner | Audience
Presentation | 15-minute Powerpoint presentation | Presentation to marketing team about new features | In-person | One time | Aamir | Marketing team
Meetings | Standup meetings | Check in about status | In-person | 2x a week | Dinesh Kumar | Project team